## Sheet1
Category	Task	Est Time	Assignee	Start time	End time
Investigate requirements	UI	0.5	K	24/09	24/09	1
	Params	0.25	K	24/09	24/09
	Constraints	0.25	K	24/09	24/09
Set up envirorment	java sgapi enviorment	0.5	K	25/09	25/09	1
	Investigate service interface	0.5	K	25/09	25/09
Design	Flow diagram	0.5	K	26/09	26/09
	sgapi interface	1.5	K	26/09	26/09
	View context model	1.5	K	26/09	26/09
Implement	sgapi interface	2	K	27/09	27/09	3
	view context model	1	K	28/09	28/09
	UI	3	K	29/09	29/09
Test	Unit test	1	K	30/09	30/09	1
Doc + present	Write docs + make presentation file	1	K	31/09	31/09	1